## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Homepage Screen | Public | Customer, Staff | This screen provide the first look for customer when they visit the website. At this page they can see what is the newest or the best selller product in our shop, the category. | Trường Minh | Updated | iter1 | iter2
2 | Header | Public | Customer, Staff | This header will show up almost every page of the website. Header will provide for user the icon for Login, and move to other page of the website. | Văn Toàn | Done | iter1 | none
3 | Footer | Public | Customer, Staff | This footer will show up almost every page of the website. Footer will provide for user the map where the shop location, and the feedback to our staff about the service. | Trường Minh | Updated | iter1 | iter2
4 | User Login Screen | Common | User | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Văn Toàn | Done | iter1 | none
5 | Product List Screen | Public, Common | Customer, Staff | This screen provide the list of product where user can click and see the detail of this product also add to cart or buy it. Search and Filter the product according to their need | Phan Quang | Updated | iter1 | iter2 | Update the buy now and add to cart button.
6 | Product Manage Screen | Private | Admin, Staff | This screen list all the item that already exist in the database for the Admin or Staff to edit, delete it. Also provide the add new product feature. | Phan Quang | Done | iter1 | iter2
7 | Forgot Password Screen | Public | Customer | Customer enter their username or email to have the captcha to reset their password. | Tuấn Thành | Done | iter1 | none
8 | Payment Screen | Public | Customer | This screen help customer check or edit their information that customer want to receive the product they ordered. | Phan Quang | Done | iter1 | iter2
9 | Sign Up Screen | Common | Customer | Customer enter their information to register. | Thanh Tùng | Done | iter1 | none
10 | Admin dashboard screen | Private | Admin, Staff | This screen show up the information about sales statistics by month, week, or best-selling products to the admin. | Thanh Tùng, | Doing | iter2 | none
11 | Sign Up | Common | Customer | This function will save the information of user when they register to the database | Thanh Tùng | Doing | iter2 | none
12 | Blog Screen | Public | Customer | This screen will show up the latest articles updated about fashion or store events. | Trường Minh | Doing | iter2 | none
13 | Blog | Public | Customer | Load the blog detail in the database which have been added by the staff or admin. | Tuấn Thành | Doing | iter2 | none
14 | Product Manage | Private | Admin, Staff | This function will provide the edit, delete, update for the product information. This function only can use by the admin or staff. | Phan Quang | Updated | iter2 | none | Fix the database error
15 | Cart Screen | Public, Common | Customer | This screen will show for the customer what they have in their cart after shopping. | Tuấn Thành | Done | iter2 | none
16 | Cart | Public, Common | Customer | Customer can add the product to cart, increase, decrease the quantity or delete the product from their cart. | Phan Quang | Updated | iter2 | none | Fix the calculate total price
17 | Login By Username vs Password | Public, Common | Customer, Staff, Admin | User enter their Email and Password to loging into the system. If Email or Password is invalid show the notification. | Văn Toàn | Done | iter2 | none
18 | Contact Screen | Public, Common | Customer | Customer can send their question to get support by staff, or get the information about the shop such as location and phone number. | Văn Toàn | To Do | iter2 | none
19 | Customer Edit Information Screen | Public, Common | Customer | This pop-up will show the information of Customer. They can change their information such as name, address, phone number | Tuấn Thành | Done | iter2 | none
20 | Payment | Common | Customer | When customer choose the home delivery option this function will save the information and the product what customer order to the database. | Phan Quang | Doing | iter2 | none
21 | Sale manage | Private | Admin, Staff | Manage data about products such as new arrivals, inventory, which items are selling well. | Thanh Tùng | To Do | iter3 | none
22 | User Manage | Private | Admin | This function will provide the edit, delete, update for the user information or user account. This function only can use by the admin. | Phan Quang | To Do | iter3 | none
23 | Product status manage | Private | Admin, Staff | This function will provide for staff the update the status of the order feature like being shipped, or successful delivery,... | Tuấn Thành | To Do | iter3 | none
24 | Homepage Manage | Private | Admin, Staff | Change the Slider and Blog what show at the Homepage. | Văn Toàn | To Do | iter3 | none
25 | Admin dashboard | Private | Admin, Staff | This function will provide the edit, delete, update for the product information. This function only can use by the admin or staff. | Trường Minh | To Do | iter3 | none
26 | Marketing manage | Private | Admin, Staff | This function will provide the edit, delete, update for the product information. This function only can use by the admin or staff. | Văn Toàn | To Do | iter3 | none
27 | Login By Email | Public | Customer | Customer can use their Email account to login to the sytem | Tuấn Thành | To Do | iter3 | iter4
28 | Login By Facebook | Public | Customer | Customer can use their Facebook account to login to the sytem | Phan Quang | To Do | iter3 | iter4

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Homepage Screen | Public | This screen provide the first look for customer when they visit the website. At this page they can see what is the newest or the best selller product in our shop, the category. | Trường Minh | Updated | II.1 | II.2
2 | Header | Public | This header will show up almost every page of the website. Header will provide for user the icon for Login, and move to other page of the website. | Văn Toàn | Done | II.1 | II.1
3 | Footer | Public | This footer will show up almost every page of the website. Footer will provide for user the map where the shop location, and the feedback to our staff about the service. | Trường Minh | Updated | II.1 | II.1
4 | User Login Screen | Common | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Văn Toàn | Done | II.2 | II.10
5 | Product List Screen | Public, Common | This screen provide the list of product where user can click and see the detail of this product also add to cart or buy it. Search and Filter the product according to their need | Phan Quang | Updated | II.1 | III.4,5
6 | Product Manage Screen | Private | This screen list all the item that already exist in the database for the Admin or Staff to edit, delete it. Also provide the add new product feature. | Phan Quang | Done | II.4 | II.23,24
7 | Forgot Password Screen | Public | Customer enter their username or email to have the captcha to reset their password. | Tuấn Thành | Done | II.2 | II.12
8 | Payment Screen | Public | This screen help customer check or edit their information that customer want to receive the product they ordered. | Phan Quang | Done | II.5 | II.7
9 | Sign Up Screen | Common | Customer enter their information to register. | Thanh Tùng | Done | II.2 | II.11
Note on G5: ====== ID#AAAAqUT3mlk KienNT (2023-02-16 11:43:42) The name of section in the SRS (software requirement specification) document
Note on H5: ====== ID#AAAAqUT3mlc KienNT (2023-02-16 11:43:42) The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Admin dashboard screen | Private | This screen show up the information about sales statistics by month, week, or best-selling products to the admin. | Thanh Tùng, | Doing | II.4 | II.32
2 | Sign Up | Common | This function will save the information of user when they register to the database | Thanh Tùng | Doing | II.2 | II.11
3 | Blog Screen | Public | This screen will show up the latest articles updated about fashion or store events. | Trường Minh | Doing | II.1 | II.2
4 | Blog | Public | Load the blog detail in the database which have been added by the staff or admin. | Tuấn Thành | Doing | II.1 | II.3
5 | Product Manage | Private | This function will provide the edit, delete, update for the product information. This function only can use by the admin or staff. | Phan Quang | Updated | II.4 | II.32
6 | Cart Screen | Public, Common | This screen will show for the customer what they have in their cart after shopping. | Tuấn Thành | Done | II.1 | II.6
7 | Cart | Public, Common | Customer can add the product to cart, increase, decrease the quantity or delete the product from their cart. | Phan Quang | Updated | II.1 | II.6
8 | Login By Username vs Password | Public, Common | User enter their Email and Password to loging into the system. If Email or Password is invalid show the notification. | Văn Toàn | Done | II.2 | II.10
9 | Contact Screen | Public, Common | Customer can send their question to get support by staff, or get the information about the shop such as location and phone number. | Văn Toàn | To Do
10 | Customer Edit Information Screen | Public, Common | This pop-up will show the information of Customer. They can change their information such as name, address, phone number | Tuấn Thành | Done | II.2 | II.14
11 | Payment | Common | When customer choose the home delivery option this function will save the information and the product what customer order to the database. | Phan Quang | Doing | II.1 | II.7
Note on G5: ====== ID#AAAAqUT3mlw KienNT (2023-02-16 11:43:42) The name of section in the SRS (software requirement specification) document
Note on H5: ====== ID#AAAAqUT3mlo KienNT (2023-02-16 11:43:42) The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
3 | Sale manage | Private | Manage data about products such as new arrivals, inventory, which items are selling well. | Thanh Tùng | Doing
4 | User Manage | Private | This function will provide the edit, delete, update for the user information or user account. This function only can use by the admin. | Phan Quang | Doing
5 | Product status manage | Private | This function will provide for staff the update the status of the order feature like being shipped, or successful delivery,... | Tuấn Thành | Doing
6 | Homepage Manage | Private | Change the Slider and Blog what show at the Homepage. | Văn Toàn | Doing
7 | Admin dashboard | Private | This function will provide the edit, delete, update for the product information. This function only can use by the admin or staff. | Trường Minh | Doing
8 | Marketing manage | Private | This function will provide the edit, delete, update for the product information. This function only can use by the admin or staff. | Văn Toàn | Doing
9 | Login By Email | Public | Customer can use their Email account to login to the sytem | Tuấn Thành | To Do
10 | Login By Facebook | Public | Customer can use their Facebook account to login to the sytem | Phan Quang | To Do
Note on G5: ====== ID#AAAAqUT3ml0 KienNT (2023-02-16 11:43:42) The name of section in the SRS (software requirement specification) document
Note on H5: ====== ID#AAAAqUT3ml4 KienNT (2023-02-16 11:43:42) The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: ====== ID#AAAAqUT3mls KienNT (2023-02-16 11:43:42) The name of section in the SRS (software requirement specification) document
Note on H5: ====== ID#AAAAqUT3mlg KienNT (2023-02-16 11:43:42) The name of section in the SDS (software design specification) document