## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Write SRS Document | Write detailed functional specification for the project | 1 |  | Closed | Trường Minh | 2023-01-26 | 2023-01-30 | iter1 | Task, 1_Doing | Document
Write SDS Document | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) project | 2 |  | Open | Văn Toàn | 2023-01-26 | 2023-02-07 | iter1 | Task, 1_Doing | Document
Integrate User Login screen with others | Integrate the User Login screen with other screens | 3 |  | Open | Tuấn Thành | 2023-01-26 | 2023-02-10 | iter1 | Task, 1_Done | User Login
Homepage Screen | This screen provide the first look for customer when they visit the website. At this page they can see what is the newest or the best selller product in our shop, the category. | 5 |  | Closed | Trường Minh | 2023-01-26 | 2023-02-10 | iter1 | Task, 1_Done | Homepage Screen
Header | This header will show up almost every page of the website. Header will provide for user the icon for Login, and move to other page of the website. | 6 |  | Closed | Văn Toàn | 2023-01-26 | 2023-02-10 | iter1 | Task, 1_Done | Header
Footer | This footer will show up almost every page of the website. Footer will provide for user the map where the shop location, and the feedback to our staff about the service. | 7 |  | Closed | Trường Minh | 2023-01-26 | 2023-02-10 | iter1 | Task, 1_Done | Footer
User Login Screen | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | 8 |  | Closed | Văn Toàn | 2023-01-26 | 2023-02-10 | iter1 | Task, 1_Done | User Login Screen
Product List Screen | This screen provide the list of product where user can click and see the detail of this product also add to cart or buy it. Search and Filter the product according to their need | 9 |  | Open | Phan Quang | 2023-01-26 | 2023-02-10 | iter1 | Task, 1_Doing | Product List Screen
Product Manage Screen | This screen list all the item that already exist in the database for the Admin or Staff to edit, delete it. Also provide the add new product feature. | 10 |  | Open | Phan Quang | 2023-01-26 | 2023-02-10 | iter1 | Task, 1_Doing | Product Manage Screen
Forgot Password Screen | Customer enter their username or email to have the captcha to reset their password. | 11 |  | Closed | Tuấn Thành | 2023-01-26 | 2023-02-10 | iter1 | Task, 1_Done | Forgot Password Screen
Payment Screen | This screen help customer check or edit their information that customer want to receive the product they ordered. | 12 |  | Open | Phan Quang | 2023-01-26 | 2023-02-10 | iter1 | Task, 1_Doing | Payment Screen
Sign Up Screen | Customer enter their information to register. | 13 |  | Closed | Thanh Tùng | 2023-01-26 | 2023-02-10 | iter1 | Task, 1_Done | Sign Up Screen
Admin dashboard screen | This screen show up the information about sales statistics by month, week, or best-selling products to the admin. | 14 |  | Open | Thanh Tùng | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Doing | Admin dashboard screen
Sign Up | This function will save the information of user when they register to the database | 15 |  | Open | Thanh Tùng | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Doing | Sign Up
Blog Screen | This screen will show up the latest articles updated about fashion or store events. | 16 |  | Open | Trường Minh | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Doing | Blog Screen
Blog | Load the blog detail in the database which have been added by the staff or admin. | 17 |  | Open | Tuấn Thành | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Doing | Blog
Product Manage | This function will provide the edit, delete, update for the product information. This function only can use by the admin or staff. | 18 |  | Open | Phan Quang | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Done | Product Manage
Fix Bug Product Manage | Fix bug Product Manage have the issues at the delete when have the error with constraint database | 19 |  | Open | Phan Quang | 2023-02-05 | 2023-01-03 | iter2 | Defect, 2_Doing | Product Manage
Cart Screen | This screen will show for the customer what they have in their cart after shopping. | 20 |  | Closed | Phan Quang | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Done | Cart Screen
Send Mail Confirm Order Bug | Can not send mail through the port of the local | 21 |  | Open | Văn Toàn | 2023-02-05 | 2023-01-03 | iter2 | Defect, 2_Doing | Cart Completion
Cart | Customer can add the product to cart, increase, decrease the quantity or delete the product from their cart. | 22 |  | Closed | Phan Quang | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Done | Cart
Login By Username vs Password | User enter their Email and Password to loging into the system. If Email or Password is invalid show the notification. | 23 |  | Closed | Văn Toàn | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Done | Login By Username vs Password
Contact Screen | Customer can send their question to get support by staff, or get the information about the shop such as location and phone number. | 24 |  | Open | Văn Toàn | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Doing | Contact Screen
Customer Edit Information Screen | This pop-up will show the information of Customer. They can change their information such as name, address, phone number | 25 |  | Open | Tuấn Thành | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Done | Customer Edit Information Screen
Payment | When customer choose the home delivery option this function will save the information and the product what customer order to the database. | 26 |  | Open | Phan Quang | 2023-02-05 | 2023-01-03 | iter2 | Task, 2_Doing | Payment
Write Project Tracking | Write Project Tracking Document for project | 27 |  | Open | Phan Quang | 2023-02-12 | 2023-02-10 | iter2 | Task, 2_Doing | Document
Write Issues Report | Write Issues Report Document for project | 28 |  | Open | Phan Quang | 2023-02-13 | 2023-02-10 | iter2 | Task, 2_Doing | Document
Successful Order | Order Successful return to the homepage and show notification | 29 |  | Open | Phan Quang | 2023-03-02 |  | iter3 | Defect 1_Doing | Document
https://docs.google.com/spreadsheets/d/14kpaYzanjGPmoMltaG5MySsDJfMbyDuX/edit?usp=sharing&ouid=103132461858819530606&rtpof=true&sd=true