## Sheet1
Total Project Tracking
Inforation in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
#NAME? | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Screen Login | Đăng nhập vào hệ thống | Admin, Staff, Customer | Log in to the system to be able to make purchases as a customer or manage as an administrator or employee | Trường Minh | Done | iter1 | iter2
2 | Screen Register | Đăng kí tài khoản | Customer | Tạo tài khoản để có thể đăng nhập bằng vai trò Customer | Thanh Tùng | Done | iter2 | none
3 | Screen Forgot password | Tìm lại mật khẩu | Customer | Tìm lại mật khẩu khi khách hàng quên mật khẩu và có thể tìm lại mật khẩu sau khi đã xác thực danh tính | Tuấn Thành | Done | iter3 | none
4 | Screen Homepage | Màn hình chính | User |  | Tử Vinh | To Do | iter4 | none
5 | Screen Homepage | Common | User |  | Tử Vinh | To Do | iter4 | none
6 | Screen Homepage | Common | User |  | Tử Vinh | To Do | iter4 | none
7 | Screen Homepage | Common | User |  | Tử Vinh | To Do | iter4 | none
8 | Screen Homepage | Common | User |  | Tử Vinh | To Do | iter4 | none